NutriScore Checkout Tool

Project Plan v2.0

NUT-04 | JHUB Africa AfyaVentures | June 2026

* Strategic Alignment: Derived from NutriScore_Requirements_v2_Evidence_Linked (NUT-04, June 2026). Every phase maps to at least one Stakeholder Need (SN-ID) and at least one functional requirement. Phase gates are defined by verifiable deliverables, not calendar milestones alone.

## 1. Standards Foundation

| Standard | Application in NUT-04 |
| --- | --- |
| ISO/IEC/IEEE 29148:2018 | Requirements engineering process: elicitation, analysis, specification, validation, verification |
| FSA-NPS 2023 (SPF workbook, 4 April 2024) | Mandatory algorithm baseline for ScoreEngine (FR-003); five-category architecture (FR-006) |
| WCAG 2.2 Level AA | Mandatory for UIWidget (NFR-007, ACC-001 to ACC-006) |
| Kenya Data Protection Act 2019 | Governs all IndexedDBCache and UserProfile operations (DATA-001 to DATA-004, SEC-001 to SEC-005) |
| Chrome Manifest V3 | ContentScript, BackgroundServiceWorker, CSP constraints (NFR-006) |
| JHUB Africa Innovation Requirements Template | Gate reviews, document structure, and sign-off requirements |

## 2. Phase Overview

| Phase | Name | Objective | Key Deliverables | SN-IDs | FRs Addressed |
| --- | --- | --- | --- | --- | --- |
| P0 | Project Foundation | Governance before requirements work | Project Charter; GitHub repo (Fivezerone/NUTRISCORE); Risk Register; Team roles | SN-001 | All (prerequisite) |
| P1 | Problem Discovery | Evidence-link the problem to science | Evidence Log EV-001-EV-008; As-Is Workflow; Root-Cause Analysis; Naivas/Carrefour DOM inspection notes | SN-002, SN-003, SN-004 | FR-001 (detection research), DATA-001 (fallback scoping) |
| P2 | Stakeholder and Domain Analysis | Ubiquitous language and stakeholder validation | Stakeholder Needs Matrix v2.0; Project Domain Model v2.0; Data Dictionary v2.0; Terminology Log | SN-001 to SN-007 | All FRs (domain model underpins all) |
| P3 | Requirements Engineering | Complete requirements baseline | NutriScore_Requirements_v2_Evidence_Linked; RTM; RVM; Use Case Catalogue; System Sequence Catalogue | SN-001, SN-005 | FR-001 to FR-013, NFR, DATA, AI, SEC, ACC |
| P4 | System Architecture Design | Execution layer architecture and adapter pattern | ADRs; Component Diagram; IRetailerAdapter interface; module dependency map | SN-007 | NFR-002, NFR-004, NFR-005, NFR-006 |
| P5 | Data and Knowledge Engineering | ScoreEngine and KenyanFallbackDatabase | ScoreEngine (2023 FSA-NPS, all 5 categories); KenyanFallbackDatabase (>=200 GroceryProducts); TC-ALG; TC-COV; Score Algorithm White Paper | SN-002, SN-003, SN-005 | FR-002, FR-003, FR-006, DATA-001 |
| P6 | UX/UI and Accessibility Design | UIWidget and Consumer journey | Figma wireframes; WCAG 2.2 AA design audit; plain-language warning text (Flesch-Kincaid <=8); Shadow DOM isolation plan | SN-004, SN-002, SN-003 | NFR-007, ACC-001 to ACC-006, AI-003, NFR-002 |
| P7 | Prototype Development | Working Chrome extension (Manifest V3) | ContentScript (MutationObserver + 300ms debounce); FoodClassifier (5-category + SPF exclusion); ScoreEngine; DiseaseEngine; AlternativesEngine; UIWidget (Preact + Shadow DOM) | SN-002 to SN-004 | FR-001 to FR-013 |
| P8 | Verification and Validation | Execute all RVM test cases | TC-ALG (20/20); TC-CAT (>=95%); TC-THR boundary matrix; TC-PERF (<2s, CLS=0); TC-COV (>=70%); TC-A11Y (Lighthouse >=90, NVDA/VoiceOver); TC-PRIV; UAT sessions | SN-001, SN-005 | All FRs, NFRs, ACC, DATA, SEC, AI |
| P9 | Pilot Deployment | Chrome Web Store deployment | Submission; Privacy Policy (ODPC-reviewed); Deployment Diagram; Extension User Guide; KNDI endorsement letter | SN-006, SN-007 | SEC-004, DATA-002, DATA-003, NFR-008 |
| P10 | Handover | Documentation and handover | Source v1.0 tag; Admin/Maintainer Guide; Test Report Bundle; Known Issues; Sustainability Plan | SN-001 | All -- final audit trail |

## 3. Phase Gate Criteria

| Gate | Phase Exit | Entry Criteria | Exit Criteria (Verifiable) | Approval Authority |
| --- | --- | --- | --- | --- |
| G0 | P0->P1 | Project charter drafted | Charter approved; team assigned; GitHub repo live | AfyaVentures Supervisor |
| G1 | P1->P2 | Evidence log started; DOM inspections done | EV-001 to EV-008 complete; root-cause analysis documented; OFacts coverage assessed | Supervisor |
| G2 | P2->P3 | Domain model drafted | Domain Model v2.0 approved; Data Dictionary v2.0 reviewed; ubiquitous language confirmed; Terminology Log complete | Supervisor + KNDI contact |
| G3 | P3->P4 | Requirements v2.0 drafted | All 9 artifacts cross-aligned; RTM complete; RVM approved; AfyaVentures and client sign-off | Supervisor + Client |
| G4 | P4->P5 | Architecture ADRs complete | IRetailerAdapter interface defined; Component Diagram approved | Supervisor |
| G5 | P5->P6 | ScoreEngine and DB built | TC-ALG 20/20 pass; >=200 KenyanFallbackDatabase entries; >=70% Naivas coverage; KNDI threshold memo signed | KNDI + Supervisor |
| G6 | P6->P7 | Figma wireframes complete | WCAG 2.2 AA design audit passed; readability confirmed; Shadow DOM plan approved | Supervisor + UX Lead |
| G7 | P7->P8 | All modules implemented | ContentScript detects products on Naivas; end-to-end badge renders within 2s | QA Lead + Supervisor |
| G8 | P8->P9 | All test cases executed | TC-ALG 20/20; TC-PERF <2s CLS=0; TC-A11Y Lighthouse>=90; TC-PRIV clean; UAT signed by AfyaVentures + KNDI | AfyaVentures + KNDI |
| G9 | P9->P10 | Web Store submitted | Submission receipt; Privacy Policy ODPC-reviewed; all diagram deliverables complete | Supervisor + ODPC review |
| G10 | P10 done | Handover checklist complete | All handover items signed off; v1.0 release tagged on GitHub | AfyaVentures |

## 4. Risk Register

| ID | Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| R-001 | ScoreEngine uses 2017 algorithm instead of 2023 revision | Medium | High | TC-ALG: 20/20 SPF reference products; CI test prevents regression; all 5 FSAProductCategory paths tested | Kibet |
| R-002 | OpenFoodFactsAPI coverage too sparse for Naivas catalogue | High | High | KenyanFallbackDatabase critical-path (>=200 entries before P7); coverage rate in Phase 5 report | Kibet |
| R-003 | FSAProductCategory misclassification produces wrong NutritionalScore | Medium | High | TC-CAT: >=95% accuracy on 50-product set; KNDI category review in P5 | Kibet |
| R-004 | DiseaseRule thresholds not validated by nutritionist | Low | High | P5 KNDI threshold review meeting; endorsement letter before Chrome Web Store submission | Kibet + AfyaVentures |
| R-005 | Chrome Web Store rejects submission on data handling | Medium | High | Submit 2 weeks before P9 deadline; Privacy Policy ODPC-reviewed before submission | Kibet |
| R-006 | UIWidget causes CLS > 0 on retailer pages | Medium | Medium | Shadow DOM CSS encapsulation; TC-CLS Lighthouse test in P8 | Kibet |